## Burn Down Chart
Project Title: Minesweeper Web Application Release #: 1 Sprint #: 1
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 4 | Day 5
| Registration-I | As a programmer I would like to create UI Mockups | Create UI Wireframe for Registration Page | Whole Team | 0.5 | 0.5
| Registration-II | As a user I would like to create a profile consisting of my basic characteristics | Design and Code the Registration Form with the User Class | Whole Team | 2 |  |  | 2
| Registration-II | As a user I would like to view a secure web page | Create the controller with HTTPPost | Whole Team | 1 |  |  | 1
| Registration-IV | As a programmer I would like to filter through unauthenticated, useless, or repetitive data sent to the server | Add Form Validators using the BaseValidator class in ASP.NET | Whole Team | 1 | [5 empty] | 1
| Registration-V | As a user I would like to be informed of an error in the form sumission process | Create Success and Error Pages that are called based on the results of the validators | Whole Team | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0
| Login-I | As a programmer I would like to create UI Mockups | Create UI Wireframe for Login Page | Whole Team | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
| Login-II | As a user I would like to input my login credentials | Design and Code the Login Form | WHole Team | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
| Login-III | As a user I would like to validate my identity | Authenticate Users based on variables given by the Login Form with the SQL database | Ivan (Brendan Observe) | 1 | 0 | 0 | 0 | 0 | 0 | 1
| Login-IV | As a user I would like to be informed of an error in the form sumission process | Create Success and Error Pages that are called based on the authentication process | Whole Team | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 7.5 | 6.25 | 5 | 3.75 | 2.5 | 1.25 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 7.5 | 6 | 6 | 3 | 2.5 | 2.5 | 0

## How To Use
Step 1 | Hold a Sprint Planning meeting on Day 1 of of your Sprint where you will complete or update your User Stories as well as (re)prioritize your User Stories in your Product Back Log (ideally this should be done for the next 3-4 Sprints)
Step 2 | Copy the User Stories you plan to complete for this Sprint into your Sprint Back Log
Step 3 | Copy the User Stories you plan to complete from your Sprint Back Log into Column C
Step 4 | Break the User Story into a series of step by step development tasks in Column D
Step 5 | Estimate the User Story (in 1, 2, 4 or 8 Effort Man Hours) in Column F and if the task is larger than 8 hours break the User Story into multiple User Stories
Step 6 | Assign the User Story to a single Team Member in Column E
Step 7 | Repeat steps 4-6 for each User Story that has been planned for this Sprint
Step 8 | At the end of each day each Team Member should update the effort hours that were worked on their User Story to burn their work down
Step 9 | After each Daily Standup each Team Member should review the Burn Down Chart to ensure your Sprint will be delivered on time